## How gender was implemented in the

## Coffee Partnership for Tanzania

By Catherine van der Wees

Amsterdam, August 2016

## Introduction

The Coffee Partnership for Tanzania is a programme co-funded by Bill and Melinda Gates Foundation (around $8 million) and three sub-grantees: Ecom Agro-industrial Corporation Ltd, Armajaro and Hanns Neumann Stiftung, managed by grantee DEG. The total costs of the progarmme is $ 25,7 million. The programme started 1 September 2012 and will continue until 31 December 2016. The goal is the programme is to empower male and female farmers to take full advantage of the opportunities arising from the production of coffee and other products. The programme aims to double the coffee production yield and to increase net income, alleviate poverty and improve livelihoods of smallholder coffee farmers in Tanzania.  The four main objectives of the initiative are:

- Increasing productivity of coffee production in an economically, environmentally and socially sustainable way;

- Strengthening links of coffee farmers to strong reliable markets, especially enabling them to profit from premiums paid for specialty and certified coffee;

- Contribute to improved production of other crops and products and enhancing the sustainability of the overall project through social and environmental measures;

- Managing the project and engaging stakeholders effectively to realize the project’s objectives.

The outreach of the programme will be 85.000 smallholder farmers. The outreach of ECOM was originally 35.000 smallholders and Armajaro is 25.000, totaling 70.000 smallholder farmers. Currently the figures for ECOM are 25.000, Armajaro is 15.000 meanwhile other partners are Hanns R Nuemann Stiftung is 25.000, DAE 10.000, Olam 5.000 and Tembo 10.000. Solidaridad and Hivos also participate in the programme, with own funding. One of the Hivos components, is the gender component working with Tutunze Kahawa Ltd (a subsidiary of ECOM), and CMS (partly owned by Armajaro). The output expected under gender component is 20 “champions” and 300 farmers (in the first three months) and 4-6 field staff trained in gender tools and system for scaling up in place.

## The gender intervention was implemented in two regions: Same, Kilimanjaro Region and two villages in Ruvuma Region: Illela and Ngima. Although ECOM left Kilimanjaro Region, Hivos continued with the gender intervention.

## The problem

In coffee production in Tanzania, women perform a lot of the work, however, most of them do not own the land, receive very little training, and have little or no say over the income from coffee, especially if they are married.  Because of this, there is little incentive for women to improve coffee, and they rather concentrate on products over which they have more control. As a consequence, coffee production stagnates and coffee programmes aimed at increasing coffee production or improving quality do not yield good results.

It does not have to be that way, it is possible to increase productivity and improve quality of coffee, and at the same time reduce gender inequalities. Below I describe the implementation of gender action programmes in Tanzania under the Coffee Partnership for Tanzania.

## The gender intervention

When the Coffee Partnership for Tanzania (CPT) was developed, ECOM and Armajaro, which was later bought by ECOM, asked Hivos to collaborate in this, and develop, among other things, a gender component.  When the programme was approved, the additional Hivos components were co-funded by the Netherlands Government. The gender intervention consisted of a number of components, spread over two years, using the Gender Action Learning Systems (GALS) approach. In October 2013, it started with an one week training of 20 farmers, (9 female and 11 male) in Same, Kilimanjaro Region, Northern Tanzania.  This was followed by community workshops in the villages where the farmers came from.

In November 2013, this was followed by similar training in Illela and Ngima, two villages in Ruvuma Region, Southern Tanzania.  In Ngima, the CMS GALS process started with a 5-day catalyst workshop. All worskhops were facilitated by Linda Mayoux, with the assistance of two champions from Bukonzo Joint Cooperative Union, which has mainstreamed the GALS approach into its organization, while Hivos and ECOM staff were trained on the job. The catalyst workshop trained 25 champions – 13 male & 12 female (15 staff and 10 farmers). As part of the Catalyst workshop there was a half day community workshop in Ngima. The community workshop was organized by the champions who brought a further 12 women and 21 men and introduced how to develop an individual vision and vision plan.

In the first training farmers learnt how to develop individual visions, plan how to achieve their vision with SMART milestones, analyse opportunities and constraints, commit to actions and trach their progress over time. They get insight whether their own situation is balanced in terms of labour, assets, decision making and expenditure behavior and determine what they want to change, and track these changes over time. They scale up the methodology through their own social networks.

In February 2014 a workshop on “Gender Strategies in Coffee in East Africa” was held in Same. The overall objective of the workshop was to share vision, strategies and experiences for promoting gender justice between different approaches and partners working in coffee in East Africa and come to an aligned approach, strategy and concrete action for CPT and 4S@scale and possibly other programmes.  In total 35 people participated, among which 16 farmers, 14 from Same, and 2 from the South of Tanzania.

In November 2014, another meeting was held in Same with the aim to do a leadership training, have a meeting with village and sub-village participants, monitor and profile the champions, and have a meeting with Same District Commissioner and District Executive Director.

In February 2015, 2 female and 2 male farmers from the three locations in Tanzania as well as 4 female and 4 male farmers from 4S@scale in Kenya came to Bukonzo Joint Cooperative Union in Western Uganda to learn from each other.

A last training was conducted in November 2015 in Illela and Ngima to develop a GALS/Good Agricultural Practices curriculum and training manual with ECOM and Hivos staff.

In Same, at the Cooperative Union level the five primary societies and the union were assisted to develop a gender balanced vision, and identify characteristics of good membership and leadership and a vision journey plan that they are in the process of implementing for increasing women’s membership and board members.  At least three of the original champions have been elected to leadership positions.

## Results

We will look at three different aspects of results: productivity and quality of coffee; gender aspects and lastly, outreach by the farmers.

## Improved productivity and quality of coffee

Many of the Tanzania champions either increased production, and/or increased the number of coffee trees.  See the profile of Mr. Amani.

Mr Amani Mberuseru was one of the first GALS champions trained in October 2013. At that time he had a very serious drinking problem and was not looking after his farm. In June 2014 he made a Vision Journey Plan for coffee, planning to increase increase production. This he achieved and has increased to 30 bags of coffee season 2014/2015, some of which he was taking to the Chome cooperative. He says he has the best coffee farm in Chome and all is because of planning through the vision journey.

Figures on productivity are available from Vuasu Cooperative Union, where the champions from Same came from.  The most active champions came from Bwanbo, Gandu and Chome, which are also the primary cooperatives with an increase in production. Vuchama and Raa, where there are either very few champions or not active, did not increase their production.  The five cooperatives involved increased coffee production by 9% and income by 12% in the 2013/4 coffee season. They currently account for 62% of the total coffee deliveries to the union.

Information: Vuasu Cooperative Union

When GALS is used in combination with other support efforts, such as training in Good Agricultural Practices, finance and access to markets, the efficiency and effectivity increases substantially.

4.2 Gender aspects

Kilimanjaro Region

In Kilimanjaro region, 200 of those taught were in the process of getting joint land agreements, adding names of women and children. More had made changes in decision making and division of labour. Very many had achieved visions on livelihoods. The training on livelihoods and leadership aroused a lot of enthusiasm. Follow up with Vuasu indicated that there had been sincere efforts to increase women’s membership of the Board.

But women were not very attracted to the role because they had too many other things to do and did not find enough incentives.

See below a story of one of the first champions, Dina, and her change process.

Dina’s story Dina is a coffee farmer, who lives in Bwambo, a tiny mountain village in the Northwest of Tanzania, near Mount Kilimanjaro and the Kenyan border. Dina had a lot of challenges when her husband died, her brother-in-law tried to force her to marry him because he wanted to take her property. Her in-laws beat her several times, knocking out her front teeth, and threatened to kill her. Her children did not continue with school due to lack of school fees. Her sons went to find local jobs. Her daughters got married at a young age. She went to court several times but the in-laws would bribe at the primary courts and win. Dina finally was helped by the government and local Vuasu cooperative staff and managed to she acquire her land. But she still had no money and was practically destitute. Looking back on that time, she says she was very depressed and with no hope for the future. Dina says her situation has improved considerably after the Gender Action Leaning for Sustainability at Scale one week champions’ training in October 2013. She gained the confidence she needed to make decisions herself and developed a long term vision. She now has direction. She has renovated her house and has 20 chickens now. She got new teeth. She has been mentored by another champion Ann Eliuza Mweta, the only female Vuasu Cooperative Board member and helped through her savings group and church group. She was also nominated to become one of the new women Vuasu Board members who were being encouraged as a result of the new Vuasu Organisational Vision Plan. She has become a respected person in Bwambo, assisting her village with her knowledge about farming. Learning changed her life and now she is changing the lives of others. She has reason to smile again, not just because of her new teeth.

Ruvuma Region

A review in June 2014 interviewed ten of the original champions, reviewed progress, and reinforced facilitation and livelihood tools.

The review found that the champions had been making significant progress towards their original visions. Through the visioning champions have bigger ambitions for themselves and more visibility in the community. This has led indirectly to their getting employment, for example, being a member of primary school committee.

The gender balance tree needed reinforcement and greater explanation. Nevertheless, whereas previously men thought they owned all the property. Now they think all property is owned equally.

From a mid-term review, done by NORC University, of the CPT in April 2015, results from focused group discussions in Illela and Ngima villages, where the gender component was implemented, are as follows:

“The GALS training was only done in two villages (Ilela and Ngima), and was a major success in both places. In Ilela, as a result of the training, men started doing household chores, and women were involved in financial decision making. Respondents said that even strangers had told them that “their farms have really changed”: “men can go buy fish, which wasn’t possible before”; “drinking has reduced”; and “some of us even own cows now.” The training has had a spillover effect on families not even involved: “they see me as a man carrying firewood and this is so surprising, they wish to join and learn.” Women and men divide coffee-related tasks: women fetch water and kill flies, men spray chemicals and do pruning, and both men and women do weeding together. One farmer said: “The man was the final decision maker…after the training this has changed, and when we look at our farms, they’ve changed compared to others nearby.”

In Ngima, results were similarly encouraging. Farmers said that cooperation between men and women is now seen as very important, especially with decisions about money. “Before the training I had no plans, it was all spur of the moment, but now I sit down and come up with an itinerary of my activities,” reported one man; another said “before I was a drunkard, but now I’ve realized my mistake and brought my wife on board.” As in Ilela, men and women divide agricultural tasks: men carry equipment and women water, and both work together to create a plan for the upcoming season”.

4.3 Outreach

By February 2015 in Vuasu, 1531 people (806 men and 725 women) had been trained in GALS by the original 20 champions.

In Ngima, of the original 12 champions, 2 had moved out of the area. The 10 remaining champions had shared the GALS methodology with 471 other people. 40 people had started Upendo Savings and Credit Group. And a new group at the TAG church had also just formed.

By April 2015 the number of champions had grown from the original 20 in June 2014 to 106 (48 women) in Illela.  New champions were not trained so well, and many of the old champions did not show so much commitment.

4.4 Interest by other stakeholders in Tanzania

In Kilimanjaro region there is strong interest from local government in rolling GALS out with local government extension workers. Strong interested in developing GALS processes and funding proposals by other local NGOs as well.

## 4.5 Other outputs

## Other outputs of the GALS process are: case studies of female and male farmers on their change processes, songs, video’s, toolkits on GALS, GALS/GAPS.

## Conclusions

The GALS processes as implemented at three locations in Tanzania under CPT have met a lot of enthusiasm by the farmers, resulted in improved quality and quantity of coffee, gender changes in relation to increased joint land ownership, joint planning and decision making, as well as better division of both productive and reproductive labour. Farmers trained were able to scale up the methodology through their own social networks.

Some quantitative and more qualitative information on the impact has been collected. However, much more could be done in a more systematic way.  Although this was planned, due to budget constraints and staff changes both at Hivos and ECOM, the process was not pursued as originally intended.

- More information

Resources developed under the Hivos CPT programme as a whole can be accessed through  http://www.galsatscale.net.

For more information also see:

http://gamechangenetwork.org/africa/tanzania/tanzania-mbinga

## http://gamechangenetwork.org/africa/tanzania/mbinga-ngima

## http://gamechangenetwork.org/africa/tanzania/vuasu-cooperative-union-same-district

## https://galsnetworkblog.net/same-vuasu/

# Footnotes

This article is an adapted version of the earlier written article: Building evidence on impact from gender action in coffee, July 2016. It is based on information provided on the various websites, given at the end of the article, under 6. More Information.

Catherine van der Wees was a Hivos employee until 1 October 2015, and responsible for the design of the gender intervention of CPT, and advised on its implementation. She is now an independent consultant. This article has been written in her personal capacity.

Sustainable and Secure Smallholder Systems at Scale. A joint programme by ECOM and Hivos, co-funded by the Netherlands Government, taking place in Kenya, Uganda and Tanzania.

https://galsnetworkblog.net/2015/07/21/amani-mberuseru-chome-vuasu-cooperative-same-tanzania/

This is an adapted version from Hivos Sustainable Food 2015: Dinah

See also http://galsnetworkblog.net/2014/09/20/dina-vuasu-champion-same-tanzania/

Source:  NORC | Coffee Partnership for Tanzania (CPT) – Focus Group Discussions Report 2015 │ Page 25